## Sheet1
Project Plan From Week 1 to completion on Week 14
Week | Date Commencing
1 | 2018-01-22 | waterfall model | TDD | Project Approach | user stories | Repositories | Back/White box testing | Functionality | Development plan | Minutes
2 | 2018-01-29 | Functionality | Project paln | User stories | white/black box testing tutorials
3 | 2018-02-05 | Project plan | User stories | Develop user stories 1, 2, 3 and DEV2 | Testing | Error checking | Error log Completion | Minutes
4 | 2018-02-12 | User stories to sprints | Set up GCM API | Summery of Push notifications and GCM | AVD configuration and problem solving |  | Error log Completion | Minutes
5 | 2018-02-19 |  |  | Researched topics discussed in meeting | Uninstalled Android studio got newer version |  | Error log Completion | Minutes
6 | 2018-02-26 | Fix Emulator | Try phone | Archetecture chapter tidy | Vancouver referencing research |  | Error log Completion | Minutes
7 | 2018-03-05 | Storm Emma | Storm Emma | Storm Emma | Storm Emma | Storm Emma | Storm Emma | Storm Emma
8 | 2018-03-12 | Write-up |  | Genymotion tester | Wrote Hello World Code | Tested Emulator | Error log Completion
9 | 2018-03-19 | Write-up |  | Finish Hello world | Start My own code again | Tested Emulator | Error log Completion
10 | 2018-03-26 | Write-up |  | Re-writeing project code |  | Tested Emulator | Error log Completion
11 | 2018-04-02 | Write-up |  | Re-writeing project code |  | Tested Emulator
12 | 2018-04-09 | Write-up |  | Re-writeing project code |  | Tested Emulator
13 | 2018-04-16 | Write-up |  | Develop user stories DEV1, 4, 5, 6 | Testing | Error checking | Error log Completion | Minutes
14 | 2018-04-23 | Write-up |  | Develop user stories 7, 8, 9 | Testing | Error checking | Error log Completion | Minutes
15 | 2018-04-30 | Write-up |  | Develop user stories 10, 11 | Testing | Error checking | Error log Completion | Minutes
16 | 2018-04-07 | Write-up | Write-up | Write-up | Write-up | Write-up | Write-up | Write-up
| Completed | Not Fully Completed | Storm Emma
Sprint 1
Sprint 2
Sprint 3