## Sheet1
Project Plan From Week 1 to completion on Week 14
Week | Date Commencing
1 | 2018-01-22 | waterfall model | TDD | Project Approach | user stories | Repositories | Back/White box testing | Functionality | Development plan | Minutes
2 | 2018-01-29 | Functionality | Project paln | User stories | white/black box testing tutorials
3 | 2018-02-05 | Project plan | User stories | Develop user stories 1, 2, 3 and DEV2 | Testing | Error checking | Error log Completion | Minutes
4 | 2018-02-12 | User stories to sprints | Set up GCM API | Summery of Push notifications and GCM | AVD configuration and problem solving |  | Error log Completion | Minutes
5 | 2018-02-19 |  |  | Develop user stories DEV1, 4 and 5 | Testing | Error checking | Error log Completion | Minutes
6 | 2018-02-26 |  |  | Develop user stories 6 | Testing | Error checking | Error log Completion | Minutes
7 | 2018-03-05 |  |  | Develop user stories 7 | Testing | Error checking | Error log Completion | Minutes
8 | 2018-03-12 |  |  | Develop user stories 8 | Testing | Error checking | Error log Completion | Minutes
9 | 2018-03-19 |  |  | Develop user stories 9 | Testing | Error checking | Error log Completion | Minutes
10 | 2018-03-26 |  |  | Develop user stories 10 | Testing | Error checking | Error log Completion | Minutes
11 | 2018-04-02 |  |  | Develop user stories 11 | Testing | Error checking | Error log Completion | Minutes
12 | 2018-04-09 |  |  | Tidy code add Extra funtionality | Testing | Error checking | Error log Completion | Minutes
13 | 2018-04-16 | Write-up | Write-up | Write-up | Write-up | Write-up | Write-up | Minutes
14 | 2018-04-23 | Write-up | Write-up | Write-up | Write-up | Write-up | Write-up | Minutes
| Completed | Not Fully Completed
Sprint 1
Sprint 2
Sprint 3